## Job
SET-UP | Cleaning | Time (h)
1
| Material Change | Time (h)
3
PREPARATION | Heating (target 60°C) | Time(h) | Energy cons (kWh) | Heating (target 80°C) | Time(h) | Energy cons (kWh)
|  | 0.25 | 0.05625 |  | 0.5 | 0.1125
| Inertization (target 0.1%) | Time(h) | Energy cons (kWh) | Gas cons (l/min)
|  | 0.417 | 0.56293 | 25
BUILD PROCESS | #JOB | Material | MACHINE1 PGreen150 |  | MACHINE2 PS150 IR |  | MACHINE3 PG150 dual IR |  | Gas cons (l/min) | Target temperature (°C) | Target oxygen (%) | Preparation time | Preparation consumption
|  |  | Energy cons (kWh) | Time (h) | Energy cons (kWh) | Time (h) | Energy cons (kWh) | Time (h)
| Job1 | Copper | 1.92 | 0.784 | 2.25 | 1.62 |  |  | 4 | 80 | 0.1 | 0.917
| Job2 | Copper | 4 | 3 | 4.1 | 5 | 4.7 | 2 | 4 | 80 | 0.1 | 0.917
| Job3 | Co-Cr |  |  | 3.5 | 5 | 3.7 | 2 | 4 | 60 | 0.1 | 0.667
| Job4 | Co-Cr |  |  | 3.6 | 12 | 4 | 7 | 4 | 60 | 0.1 | 0.667
| Job5 | Inconel |  |  | 3.6 | 62 | 4.1 | 50 | 4 | 60 | 0.1 | 0.667
| Job6 | Inconel |  |  | 3.5 | 8 | 4 | 7 | 4 | 60 | 0.1 | 0.667
| Job7 | Copper | 4.1 | 13 | 3.6 | 21 | 4 | 13 | 4 | 80 | 0.1 | 0.917
| Job8 | Copper alloy | 4.1 | 11 | 3.6 | 24 | 4.1 | 13 | 4 | 80 | 0.1 | 0.917

## Production Schedule
| Monday | [12 empty] | Tuesday | [11 empty] | Wednesday
| 00 - 09 | 09 - 10 | 10 - 11 |  | 11 - 12 | 12 - 13 | 13 - 14 | 14 - 15 | 15 - 16 | 16 - 17 |  | 17 - 18 | 18 - 24 | 00 - 09 | 09 - 10 | 10 - 11 |  | 11 - 12 | 12 - 13 | 13 - 14 | 14 - 15 | 15 - 16 | 16 - 17 | 17 - 18 | 18 - 24 | 00 - 09 | 09 - 10 |  | 10 - 11 | 11 - 12 | 12 - 13 | 13 - 14 | 14 - 15 | 15 - 16 | 16 - 17 | 17 - 18 | 18 - 24
Job1 | [7 empty] | PGr150
Job2 | [16 empty] | PGr150
Job3 |  |  |  | PS150
Job4 | [12 empty] | PS150
Job5 | [5 empty] | PGe150
Job6 | [21 empty] | Material Change | [5 empty] | PS150
Job7 | [10 empty] | PGr150
Job8 | [16 empty] | Material Change |  |  |  |  | PGr150
| Hypothesis | [7 empty] | Legend
| Work 5 days per week, from Monday to Friday | [7 empty] | Set up
| 8 hours per day, from 9 to 13 and from 14 to 18 | [7 empty] | Preparation
| 1 machine operator | [7 empty] | Build process
| Monday | [12 empty] | Tuesday | [11 empty] | Wednesday
| 00 - 09 | 09 - 10 | 10 - 11 |  | 11 - 12 | 12 - 13 | 13 - 14 | 14 - 15 | 15 - 16 | 16 - 17 |  | 17 - 18 | 18 - 24 | 00 - 09 | 09 - 10 | 10 - 11 |  | 11 - 12 | 12 - 13 | 13 - 14 | 14 - 15 | 15 - 16 | 16 - 17 | 17 - 18 | 18 - 24 | 00 - 09 | 09 - 10 |  | 10 - 11 | 11 - 12 | 12 - 13 | 13 - 14 | 14 - 15 | 15 - 16 | 16 - 17 | 17 - 18 | 18 - 24 | Legend
PGr150 | [7 empty] | Job1 |  |  | Job7 | [5 empty] | Job2 |  |  |  |  | Job8 | [16 empty] | Copper
PS150 |  |  |  | Job3 | [8 empty] | Job4 | [8 empty] | Material Change | [5 empty] | Job6 | [9 empty] | Set up | Co-Cr
PGe150 | [5 empty] | Job5 | [31 empty] | Preparation | Inconel
Operator | [16 empty] | Material Change |  |  |  |  | Material Change | [16 empty] | Copper alloy
Work 5 days per week, from Monday to Tuesday
8 hours per day, from 9 to 13 and from 14 to 18
Starting to count from 1 as Monday at 9, the best moment to finish a job is hours 1 - 4, 6 - 9 and + (24*1, 24*2, 24*3, 24*4)
1 machine operator
Most time consuming job is Job5
Job 3 at PSharp150
Monday 9 - 10.30 - 15.30
Job5 at PGenius150
Monday 10.30 - 12 - Wednesday 14
Job 1 Pgreen
12 - 14 - 15
Job 7 at Pgreen150
15 - 16.30 - Tuesday 5.30
Job 4 at Psharp150
16,30 - 18 - Tuesday 6
|  | Job2 at Pgreen150 |  |  | Tuesday
9 - 10.30 - 13,30
Job 8 at PGreen150
10.30 - 15 - Wednesday 2
Job 6 at PSharp150
15 - 9.30 Wednesday - 17.30

## Sheet1
Resource | Monday | [12 empty] | Tuesday | [11 empty] | Wednesday
| 00 - 09 | 09 - 10 | 10 - 11 |  | 11 - 12 | 12 - 13 | 13 - 14 | 14 - 15 | 15 - 16 | 16 - 17 |  | 17 - 18 | 18 - 24 | 00 - 09 | 09 - 10 | 10 - 11 |  | 11 - 12 | 12 - 13 | 13 - 14 | 14 - 15 | 15 - 16 | 16 - 17 | 17 - 18 | 18 - 24 | 00 - 09 | 09 - 10 |  | 10 - 11 | 11 - 12 | 12 - 13 | 13 - 14 | 14 - 15 | 15 - 16 | 16 - 17 | 17 - 18 | 18 - 24 | Legend
PGr150 | [7 empty] | Job1 |  |  | Job7 | [5 empty] | Job2 |  |  |  |  | Job8 | [16 empty] | Copper
PS150 |  |  |  | Job3 | [8 empty] | Job4 | [8 empty] | Material Change | [5 empty] | Job6 | [9 empty] | Set up | Co-Cr
PGe150 | [5 empty] | Job5 | [31 empty] | Preparation | Inconel
Operator | [21 empty] | Material Change | [16 empty] | Copper alloy